## Data Validation
when? | Table | Field | Type | Read/Write | Data Source | Constraints | TestID | Pass/Fail
On signin | users | name | String | w | Spotify |  | DB01
On signin | users | id | String | w | Spotify |  | DB02
To get spotify recommendations | users | preferences | [PreferenceSchema] | r | written by DB05 (Spotify) | array length? | DB03
after getting recommendations | playlist | queue | [SongSchema] | w | Spotify | array length? | DB04
while listening to song | users | preferences | [PreferenceSchema] | w | Spotify | array length? | DB05
after song finishes, if song is enjoyed | playlist | songs | [SongSchema] | w | Spotify | array length? | DB06
after song finishes | playlist->queue | uri | string | r | written by DB04 (Spotify) |  | DB07

## UI Validation
Page Name | UI Element | Expected Function | Test ID | Pass/Fail
index | Home Button | Navigate to homepage | UI01 | P
index | About Button | Navigate to "about" section on homepage | UI02 | P
index | Upper Explore Button | Navigate to "play" page | UI03 | P
index | Green Triangle icon | Navigate to homepage | UI04 | P
index | Lower Explore Button | Navigate to "play" page | UI05 | F
index | "see the source" button | redirect to github repo | UI06 | F

## Remediation
BugID | TestID | Description | Severity | Assigned | Completion Date
UIB01 | UI05 | Lower explore button on homepage unresponsive | 2 | Jinghu
UIB02 | UI06 | See the Source button on homepage unresponsive | 1 | Jinghu